CMI NaaP AI Network Intelligence

Implementation Roadmap

Portfolio Implementation Roadmap

Prepared by: Alpit Tare

Date: March 22, 2026 | Version: 1.0

# CMI NaaP AI Network Intelligence: Implementation Roadmap & Timeline

## Executive Summary

This document outlines the 12-month implementation roadmap for the CMI NaaP AI Network Intelligence project portfolio, spanning 6 projects across 4 strategic phases. The roadmap balances capability delivery, resource optimization, and dependency management to achieve full operational intelligence across the network.

Portfolio Scope:

- Predictive Capacity Intelligence (PCI)

- Incident Correlation & Root Cause Analysis (ICR)

- Autonomous Operations Agent (AOA)

- Self-Healing Network (SHN)

- Blast Radius Analysis (BRA)

- Network Knowledge Assistant (NKA)

Strategic Timeline: Q2 2026 – Q1 2027 (12 months)

---

## 1. Roadmap Overview

### 1.1 Phase Structure

┌─────────────────────────────────────────────────────────────────────┐
│  PHASE 1: FOUNDATION (Months 1-3)                                   │
│  Focus: Predictive Capacity, Incident Correlation                   │
│  Goal: Establish analytics layer & event understanding              │
└─────────────────────────────────────────────────────────────────────┘
                            ↓
┌─────────────────────────────────────────────────────────────────────┐
│  PHASE 2: INTELLIGENCE (Months 3-6)                                 │
│  Focus: Autonomous Operations Agent, Self-Healing Network           │
│  Goal: Enable autonomous remediation & self-healing capabilities    │
└─────────────────────────────────────────────────────────────────────┘
                            ↓
┌─────────────────────────────────────────────────────────────────────┐
│  PHASE 3: CRITICAL CAPABILITIES (Months 6-9)                        │
│  Focus: Blast Radius Analysis (new capability)                      │
│  Goal: Enable impact-driven decision making                         │
└─────────────────────────────────────────────────────────────────────┘
                            ↓
┌─────────────────────────────────────────────────────────────────────┐
│  PHASE 4: KNOWLEDGE LAYER (Months 9-12)                             │
│  Focus: Network Knowledge Assistant, Integration                    │
│  Goal: Unified knowledge platform, end-to-end intelligence          │
└─────────────────────────────────────────────────────────────────────┘

### 1.2 High-Level Milestones

| Phase | Duration | Primary Deliverable | Go/No-Go Gate | Demo Env Available |
| --- | --- | --- | --- | --- |
| Phase 1 | M1-3 | Analytics Foundation | M3 (Week 12) | ✓ Yes (M2) |
| Phase 2 | M3-6 | Autonomous Operations | M6 (Week 24) | ✓ Yes (M4) |
| Phase 3 | M6-9 | Impact Analysis | M9 (Week 36) | ✓ Yes (M7) |
| Phase 4 | M9-12 | Unified Intelligence | M12 (Week 48) | ✓ Yes (M10) |

---

## 2. Phase 1: Foundation (Months 1-3)

### 2.1 Strategic Objectives

- Establish analytics foundation for network intelligence

- Deploy real-time incident detection and correlation

- Create baseline capacity forecasting capability

- Validate data pipeline and integration architecture

- Achieve demo-ready state with core observability

### 2.2 Project Assignments

### 2.2.1 Predictive Capacity Intelligence (PRIMARY) — 60% Support

Goal: Deploy capacity forecasting engine; establish ML/data pipeline

Deliverables:

- Data Integration Layer (Week 1-3)

  - Ingest historical capacity metrics (compute, storage, bandwidth)

  - Validate data quality, identify gaps

  - Establish time-series database (e.g., InfluxDB, TimescaleDB)

  - Effort: 120 person-hours

  - Dependency: Network data access, historical metrics

- Baseline Forecast Models (Week 4-8)

  - Statistical forecasting (ARIMA, exponential smoothing)

  - ML models (LSTM time-series prediction)

  - Model evaluation framework (RMSE, MAE, coverage)

  - Effort: 160 person-hours

  - Deliverable: Initial 1-month lookahead forecasts

- Forecast API & Dashboard (Week 9-12)

  - REST API for capacity queries (by resource, by timeline)

  - Web dashboard for visualization (trends, anomalies, thresholds)

  - Alerting triggers for capacity concerns (>85% utilization forecasted)

  - Effort: 100 person-hours

  - Deliverable: Production-ready API, demo dashboard

Staffing:

- 2 Data Scientists (full-time) — Model development

- 1 Data Engineer (full-time) — Data pipeline

- 1 Backend Engineer (50%) — API development

- 1 DevOps Engineer (30%) — Infrastructure

Total Effort: 380 person-hours

Budget: $75K (salaries + infrastructure)

Success Criteria:

- ✓ Forecasts within 10% accuracy vs. actual (MAPE < 10%)

- ✓ API response time < 500ms (p95)

- ✓ Data freshness < 1 hour

- ✓ Dashboard accessible to 50+ internal users

---

### 2.2.2 Incident Correlation & RCA (PRIMARY) — 60% Support

Goal: Deploy real-time incident detection and correlation engine

Deliverables:

- Event Ingestion & Normalization (Week 1-4)

  - Connectors for syslog, SNMP, API polling, event streams

  - Event schema normalization (timestamp, source, event type, severity)

  - Deduplication and preprocessing

  - Effort: 140 person-hours

  - Dependency: Network monitoring infrastructure (Prometheus, Grafana, etc.)

- Correlation Engine (Week 5-9)

  - Rules-based correlation (event patterns, time windows, source proximity)

  - ML-based correlation (unsupervised clustering, anomaly detection)

  - Incident grouping and timeline reconstruction

  - Effort: 180 person-hours

  - Deliverable: Correlated incident groups in real-time

- Root Cause Analysis (RCA) Engine (Week 10-12)

  - Dependency graph analysis (which failed component likely caused others)

  - Historical pattern matching (similar incidents, known causes)

  - RCA hypothesis generation and ranking

  - Effort: 120 person-hours

  - Deliverable: Top-3 RCA hypotheses per incident

Staffing:

- 1 Incident Intelligence Architect (full-time)

- 2 Data Engineers (full-time) — Event pipeline

- 1 ML Engineer (50%) — Correlation algorithms

- 1 Backend Engineer (50%) — API/UI

Total Effort: 440 person-hours

Budget: $85K (salaries + infrastructure)

Success Criteria:

- ✓ Event ingestion latency < 5 seconds (p95)

- ✓ Correlation accuracy > 85% (validated against manual grouping)

- ✓ RCA top-1 accuracy > 60% (correct root cause in top suggestion)

- ✓ Dashboard accessible to 30+ on-call engineers

---

### 2.2.3 Supporting Activities

Blast Radius Analysis (10% resource)

- Scope topology data model for Phase 3

- Establish baseline network topology data source

- Effort: 40 person-hours

Autonomous Operations Agent (5% resource)

- Preliminary policy framework design

- Mock integration tests with ICR

- Effort: 20 person-hours

---

### 2.3 Phase 1 Resource Allocation

Total Portfolio Effort (Phase 1): 920 person-hours
Breakdown by Project:
  - Predictive Capacity Intelligence:  380 ph (41%)
  - Incident Correlation & RCA:        440 ph (48%)
  - BRA (scoping):                      40 ph (4%)
  - AOA (design):                       20 ph (2%)
  - Support/Infrastructure:             40 ph (5%)
 
Staffing Summary:
  - Data Scientists:          2 FTE
  - ML Engineers:             1.5 FTE (50% shared)
  - Data Engineers:           3 FTE
  - Backend Engineers:        2 FTE (50% shared)
  - DevOps/Infrastructure:    1 FTE (30% shared)
  - Architects/Leadership:    1 FTE
 
Total Team Size: ~11 FTE

### 2.4 Phase 1 Dependencies & Assumptions

Internal Dependencies:

- Data pipeline (PCI → ICR): Incident data feeds into capacity forecasts for anomaly detection

- Monitoring infrastructure readiness (required for event ingestion)

External Dependencies:

- Network team provides topology data access

- Monitoring team provides raw event streams

- Infrastructure team provisions compute resources (Kubernetes cluster, databases)

Key Assumptions:

- Historical capacity data available and clean (>95% quality)

- Event streams available in real-time (latency < 5 sec)

- No major network reorganization during Phase 1

### 2.5 Demo Environment Timeline (Phase 1)

Target Go-Live: End of Month 2 (Week 8)

| Week | Component | Demo-Ready Status | Audience |
| --- | --- | --- | --- |
| W3 | PCI Data pipeline | ✓ Data flowing | Data team |
| W5 | ICR Event ingestion | ✓ Real events collected | Monitoring team |
| W7 | PCI Forecast API | ✓ Queries returning forecasts | Analytics team |
| W8 | Public Demo | ✓ Both APIs + dashboards live | Stakeholders (30+) |

Demo Script (M2 Public Demo):

- Show live network capacity trends (PCI dashboard)

- Trigger a synthetic incident, show correlation in real-time (ICR)

- Display RCA hypotheses for correlated incident

- Show forecast alerting (capacity trending toward threshold)

- Q&A with stakeholders

---

## 3. Phase 2: Intelligence (Months 3-6)

### 3.1 Strategic Objectives

- Deploy autonomous remediation capabilities (AOA)

- Enable self-healing network operations (SHN)

- Integrate PCI and ICR with operational decision-making

- Scale incident correlation to production volumes

- Achieve autonomous operations in controlled scenarios

### 3.2 Project Assignments

### 3.2.1 Autonomous Operations Agent (PRIMARY) — 70% Support

Goal: Deploy automated remediation policies; enable closed-loop operations

Deliverables:

- Policy Framework & Engine (Week 13-18)

  - Policy definition language (DSL or YAML-based rules)

  - Policy evaluation engine (trigger conditions, actions)

  - Action execution framework (API calls, workflows, tickets)

  - Audit logging (what was executed, why, by whom/what)

  - Effort: 200 person-hours

  - Dependency: ICR incident data, PCI capacity forecasts

- Initial Policy Library (Week 19-22)

  - 15-20 core remediation policies (high confidence, low risk)

  - Examples:

  - "If CPU > 90% for 5 min, trigger cost-optimized scaling"

  - "If packet loss > 5%, initiate link diagnostics"

  - "If memory pressure high, restart low-priority services"

  - "If API latency degraded, enable request throttling"

  - Effort: 120 person-hours

  - Validation: Manual review + staging environment testing

- Feedback Loop & Learning (Week 23-24)

  - Action outcome tracking (did remedy work?)

  - Policy effectiveness scoring (success rate, blast radius)

  - Adaptive thresholds (self-tuning based on outcome history)

  - Effort: 80 person-hours

  - Deliverable: Closed-loop operational learning

- Human-in-the-Loop Approval (Week 13-24, integrated)

  - Decision review queue (high-risk actions require approval)

  - Approval UI and notifications

  - Escalation rules (if approval not given in N minutes, notify manager)

  - Effort: 60 person-hours

Staffing:

- 1 Senior Operations Architect (full-time)

- 2 Backend Engineers (full-time) — Policy engine

- 1 Frontend Engineer (50%) — Approval UI

- 1 QA/Test Engineer (50%) — Validation

- 1 Product Manager (30%)

Total Effort: 460 person-hours

Budget: $95K

Success Criteria:

- ✓ Policy engine throughput > 1000 evaluations/sec

- ✓ Action execution latency < 2 seconds (p95)

- ✓ Policy effectiveness score > 75% (actions achieve intended outcome)

- ✓ Zero critical failures (policies causing major outages)

- ✓ Operator approval queue SLA < 5 minutes for urgent

---

### 3.2.2 Self-Healing Network (PRIMARY) — 70% Support

Goal: Deploy automated healing workflows; enable self-recovery

Deliverables:

- Healing Workflow Engine (Week 13-19)

  - Workflow definition (multi-step orchestration, conditional branches)

  - Action library (reboot component, restart service, reroute traffic, etc.)

  - Rollback capability (if healing makes things worse, undo)

  - Effort: 180 person-hours

  - Dependency: AOA policy framework, existing orchestration tools

- Initial Healing Playbooks (Week 20-24)

  - 10-15 core healing workflows

  - Examples:

  - "BGP convergence failure" → Check peer configs, reset BGP session, verify routes

  - "Memory leak detected" → Isolate process, capture heap dump, graceful restart

  - "Link flap storm" → Increase dampening, remove faulty link from rotation, alert

  - "DNS resolution timeout" → Switch to secondary resolver, notify DNS team

  - Effort: 140 person-hours

  - Validation: Staging + canary deployment

- Health State Monitoring (Week 13-24, integrated)

  - Real-time health metrics (component status, capability metrics)

  - Health scoring algorithm (composite health from multiple signals)

  - Health state transitions (unknown → degraded → critical → healed)

  - Effort: 100 person-hours

- Rollback & Safety (Week 13-24, integrated)

  - Transaction-like semantics (healing as atomic operation)

  - Rollback triggers (if health worsens post-healing, revert)

  - Risk scoring (estimate blast radius of healing action before execution)

  - Effort: 80 person-hours

Staffing:

- 1 Network Reliability Architect (full-time)

- 2 Backend Engineers (full-time) — Workflow engine

- 1 Network Engineer (50%) — Playbook development

- 1 QA/Test Engineer (50%) — Validation in staging

Total Effort: 500 person-hours

Budget: $105K

Success Criteria:

- ✓ Workflow execution success rate > 85%

- ✓ Healing latency < 30 seconds (from issue detected to action initiated)

- ✓ Rollback success rate > 95% (if triggered)

- ✓ Zero unintended consequences from healing actions (blast radius = 0)

- ✓ 80%+ of healing actions require no escalation to humans

---

### 3.2.3 Predictive Capacity Intelligence (SECONDARY) — 30% Support

Goal: Enhance models; integrate with AOA for capacity-driven remediation

Activities:

- Model retraining on Phase 1 operational data

- Explainability framework (why did forecast change?)

- Integration with AOA (capacity forecast triggers scaling policies)

- Effort: 120 person-hours

- Staffing: 1 Data Scientist (part-time), 1 Backend Engineer (30%)

---

### 3.2.4 Incident Correlation & RCA (SECONDARY) — 30% Support

Goal: Scale to production volumes; improve RCA accuracy

Activities:

- Performance optimization (handle 10x event volume)

- RCA model refinement using Phase 1 incident outcomes

- Integration with AOA (RCA insights feed into policy tuning)

- Effort: 140 person-hours

- Staffing: 1 ML Engineer (50%), 1 Data Engineer (50%)

---

### 3.3 Phase 2 Resource Allocation

Total Portfolio Effort (Phase 2): 1,320 person-hours
Breakdown by Project:
  - Autonomous Operations Agent:       460 ph (35%)
  - Self-Healing Network:              500 ph (38%)
  - Predictive Capacity Intelligence:  120 ph (9%)
  - Incident Correlation & RCA:        140 ph (11%)
  - Support/Infrastructure:             100 ph (7%)
 
Staffing Summary:
  - Senior Architects:        2 FTE
  - Backend Engineers:        4 FTE
  - Frontend Engineers:       0.5 FTE
  - Network Engineers:        0.5 FTE
  - Data Scientists/ML:       1.5 FTE
  - Data Engineers:           1 FTE
  - QA/Test Engineers:        1 FTE
  - Product/Leadership:       1 FTE
 
Total Team Size: ~12 FTE (overlapping with Phase 1)

### 3.4 Phase 2 Dependencies

Critical Path:

- Phase 1 completion (ICR, PCI operational)

- AOA policy framework complete before SHN integration

- Network team approval of remediation policies before live execution

Integration Points:

- AOA ← ICR (incident triggers policy evaluation)

- AOA ← PCI (capacity forecast triggers scaling policies)

- SHN ← AOA (healing workflows leverage AOA policy engine)

- SHN ← ICR (incident correlation informs healing playbook selection)

### 3.5 Demo Environment Timeline (Phase 2)

Target Go-Live: End of Month 4 (Week 20)

| Week | Component | Status | Audience |
| --- | --- | --- | --- |
| W15 | AOA Policy engine | ✓ Policies evaluated | Ops team |
| W18 | SHN Workflow engine | ✓ Workflows executed in staging | SRE team |
| W19 | AOA + SHN integration | ✓ End-to-end healing triggered by policies | Engineering leadership |
| W20 | Public Demo | ✓ Live autonomous remediation | Executive stakeholders (40+) |

Demo Script (M4 Public Demo):

- Show policy library and effectiveness metrics

- Simulate network degradation (packet loss, latency spike)

- Watch incident correlation in ICR (automatic grouping)

- Show AOA policy evaluation → recommend remediation

- Operator approves; SHN executes healing workflow

- Show real-time health recovery post-healing

- Rollback triggers and recovers (if needed)

- RCA insights and policy feedback loop

- Q&A

---

## 4. Phase 3: Critical Capabilities (Months 6-9)

### 4.1 Strategic Objectives

- Deploy Blast Radius Analysis capability (new, critical)

- Enhance impact-driven decision making

- Optimize autonomous operations based on blast radius

- Scale to full production capacity

- Achieve enterprise-grade governance

### 4.2 Project Assignments

### 4.2.1 Blast Radius Analysis (PRIMARY) — 75% Support

Goal: Deploy impact analysis engine; enable risk-aware decision making

Deliverables:

- Topology Data Model & Ingest (Week 25-29)

  - Network topology schema (devices, links, services, dependencies)

  - Data sources: IPAM, configuration management DB, service catalog

  - Real-time topology synchronization (detect changes)

  - Effort: 160 person-hours

  - Dependency: Network infrastructure data access

- Impact Analysis Engine (Week 30-35)

  - Dependency graph modeling (service → resources → infrastructure)

  - Failure propagation simulation (if X fails, what breaks?)

  - Impact scoring (# services affected, # users impacted, revenue impact)

  - Root cause → consequence mapping

  - Effort: 200 person-hours

  - Algorithms: Graph traversal, criticality scoring, probabilistic impact

- Blast Radius Risk Scoring (Week 36-37)

  - Risk = (likelihood of failure) × (blast radius)

  - Likelihood from ICR (historical incident frequency)

  - Blast radius from BRA (failure impact)

  - Risk-aware policy recommendations (AOA integration)

  - Effort: 100 person-hours

- API & Visualization (Week 25-37, integrated)

  - REST API for impact queries (by resource, by service)

  - Visualization: dependency graph, impact heatmap, risk matrix

  - "What-if" simulation UI (predict impact of proposed change)

  - Effort: 140 person-hours

Staffing:

- 1 Graph Database/Analytics Architect (full-time)

- 1 Backend Engineer (full-time) — Impact engine

- 1 Backend Engineer (50%) — API development

- 1 Frontend Engineer (50%) — Visualization

- 1 Data Engineer (50%) — Topology data pipeline

Total Effort: 600 person-hours

Budget: $120K

Success Criteria:

- ✓ Topology ingest latency < 30 seconds (detect changes)

- ✓ Impact query latency < 1 second (p95)

- ✓ Impact accuracy > 80% (vs. actual incident blast radius)

- ✓ Risk scoring correlation > 0.75 with actual incident severity

- ✓ What-if simulation supports < 5 second response

---

### 4.2.2 Autonomous Operations Agent (SECONDARY) — 20% Support

Goal: Integrate blast radius into policy optimization

Activities:

- Risk-aware policy tuning (favor low-blast-radius actions)

- Policy effectiveness scoring enhancements (consider impact)

- Automated policy rollout (low-risk policies to production faster)

- Effort: 100 person-hours

- Staffing: 1 Senior Architect (20%), 1 Backend Engineer (50%)

---

### 4.2.3 Self-Healing Network (SECONDARY) — 15% Support

Goal: Risk-aware healing (consider blast radius before executing)

Activities:

- Integrate BRA impact queries into healing decision logic

- Add rollback triggers based on blast radius thresholds

- Effort: 80 person-hours

---

### 4.2.4 Governance & Lifecycle Framework

Goal: Establish data retention, deletion, and lifecycle policies

Deliverables:

- Data retention policies (by entity type: incidents, forecasts, policies)

- Soft-delete + audit trail implementation

- Automated cleanup jobs (monthly purge of archived data)

- Compliance reporting framework

- Effort: 150 person-hours

- Staffing: 1 Data Architect (full-time), 1 DevOps (50%)

---

### 4.3 Phase 3 Resource Allocation

Total Portfolio Effort (Phase 3): 930 person-hours
Breakdown by Project:
  - Blast Radius Analysis:             600 ph (65%)
  - Governance/Lifecycle:              150 ph (16%)
  - AOA Integration:                   100 ph (11%)
  - SHN Integration:                    80 ph (8%)
 
Staffing Summary:
  - Graph/Analytics Architects:  1 FTE
  - Backend Engineers:           2 FTE
  - Frontend Engineers:          0.5 FTE
  - Data Engineers:              1 FTE
  - DevOps/Infrastructure:       1.5 FTE
 
Total Team Size: ~6 FTE (smaller team, focused)

### 4.4 Phase 3 Dependencies

Critical Path:

- Phase 2 completion (AOA, SHN operational)

- Topology data access from network infrastructure

- BRA API complete before AOA/SHN integration

Integration Points:

- AOA ← BRA (policy execution considers blast radius)

- SHN ← BRA (healing decision considers impact)

- All projects ← Governance (lifecycle policies apply across portfolio)

### 4.5 Demo Environment Timeline (Phase 3)

Target Go-Live: End of Month 7 (Week 32)

| Week | Component | Status | Audience |
| --- | --- | --- | --- |
| W28 | BRA Topology model | ✓ Network topology synchronized | Network team |
| W31 | BRA Impact engine | ✓ Queries return impact scores | Architecture team |
| W32 | Public Demo | ✓ What-if analysis, risk-aware policies | CTO, Operations leadership (50+) |

Demo Script (M7 Public Demo):

- Show network topology visualization

- Select a critical infrastructure component (e.g., core router)

- Run impact simulation (what services would fail if this fails?)

- Show risk scoring (likelihood × blast radius)

- Demonstrate AOA policy respects blast radius (low-risk policies prioritized)

- Show healing decision with impact consideration

- Before/after blast radius comparison (how topology change affects risk)

- Q&A

---

## 5. Phase 4: Knowledge Layer (Months 9-12)

### 5.1 Strategic Objectives

- Deploy Network Knowledge Assistant (NKA) as unified intelligence layer

- Integrate all projects into cohesive intelligence platform

- Enable self-learning and continuous improvement

- Achieve enterprise-scale knowledge management

- Establish AI-driven decision support culture

### 5.2 Project Assignments

### 5.2.1 Network Knowledge Assistant (PRIMARY) — 80% Support

Goal: Deploy unified knowledge platform; enable semantic AI-driven insights

Deliverables:

- Knowledge Graph Architecture (Week 37-41)

  - Entities: network components, incidents, policies, forecasts, configurations

  - Relationships: causes, depends-on, similar-to, triggers, evolves-from

  - Entity resolution (map same entities across projects)

  - Versioning and provenance tracking

  - Effort: 200 person-hours

  - Technology: Neo4j or Amazon Neptune

- Knowledge Ingestion Pipeline (Week 42-45)

  - Automatic extraction from:

  - Incident RCAs (ICR) → root cause entities + relationships

  - Blast radius analyses (BRA) → impact relationships

  - Healing outcomes (SHN) → effectiveness knowledge

  - Capacity trends (PCI) → forecast reliability patterns

  - Policy outcomes (AOA) → effectiveness + side effects

  - Deduplication and enrichment (NLP entity tagging)

  - Effort: 160 person-hours

- Semantic Search & Retrieval (Week 46-49)

  - Vector embedding for knowledge entries (semantic similarity)

  - Hybrid search (keyword + semantic)

  - Query interface (natural language questions)

  - Related knowledge suggestions (context-aware recommendations)

  - Effort: 140 person-hours

- Knowledge-Driven Decision Support (Week 50-52)

  - Incident → suggest resolution based on similar past incidents

  - Change → predict impact using historical knowledge

  - Anomaly → explain using known patterns

  - Effort: 120 person-hours

- UI & Experience (Week 37-52, integrated)

  - Web interface for knowledge exploration

  - Slack/Teams integration (ask questions from chat)

  - Notifications (new knowledge that affects running operations)

  - Effort: 100 person-hours

Staffing:

- 1 Knowledge Graph Architect (full-time)

- 1 ML/NLP Engineer (full-time) — Semantic search, embeddings

- 2 Backend Engineers (full-time) — Ingestion pipeline, APIs

- 1 Frontend Engineer (full-time) — UI/UX

- 1 Data Engineer (50%) — ETL pipelines

Total Effort: 720 person-hours

Budget: $145K

Success Criteria:

- ✓ Knowledge graph contains >100K entities with >500K relationships

- ✓ Semantic search accuracy > 85% (relevant results in top 5)

- ✓ Incident resolution suggestion accuracy > 70%

- ✓ Change impact prediction accuracy > 75%

- ✓ User adoption > 60% of engineering team (daily active users)

- ✓ NKA resolves >40% of incidents autonomously (without escalation)

---

### 5.2.2 Integration & Excellence

Goal: Ensure seamless integration across all 6 projects

Deliverables:

- Portfolio Integration Harness (Week 37-52)

  - Unified API gateway (single endpoint for all projects)

  - Event pipeline integration (all projects subscribe to relevant events)

  - Shared authentication/authorization

  - Effort: 100 person-hours

- Cross-Project Learning (Week 37-52)

  - Incident insights feed back to PCI (capacity anomalies)

  - Capacity forecasts inform policy thresholds (AOA)

  - Policy effectiveness metrics inform healing strategies (SHN)

  - Healing outcomes improve RCA models (ICR)

  - Effort: 80 person-hours

- Operations Handbook & Runbooks (Week 37-52)

  - Document best practices and procedures

  - Automated runbook generation from policies + healing workflows

  - Effort: 60 person-hours

Staffing:

- 1 Senior Integration Architect (full-time)

- 1 Backend Engineer (50%)

- 1 Technical Writer (50%)

Total Effort: 240 person-hours

---

### 5.2.3 All Projects (SUPPORT) — Continuous Improvement

Goal: Optimize and refine based on operational experience

Activities per Project:

- PCI: Model performance tuning, expand forecast window

- ICR: Correlation accuracy improvements, RCA refinement

- AOA: Policy library expansion (30→50+ policies), risk scoring

- SHN: Playbook expansion (15→25+ playbooks), rollback enhancements

- BRA: Topology accuracy improvements, impact scoring refinement

Staffing: 1 FTE per project (distributed across team)

Total Effort: 300 person-hours

---

### 5.3 Phase 4 Resource Allocation

Total Portfolio Effort (Phase 4): 1,260 person-hours
Breakdown by Project:
  - Network Knowledge Assistant:       720 ph (57%)
  - Integration & Excellence:          240 ph (19%)
  - Continuous Improvement (all):      300 ph (24%)
 
Staffing Summary:
  - Knowledge Graph Architect:  1 FTE
  - ML/NLP Engineers:           1 FTE
  - Backend Engineers:          3 FTE
  - Frontend Engineers:         1 FTE
  - Data Engineers:             0.5 FTE
  - Integration/DevOps:         0.5 FTE
  - Technical Writers:          0.5 FTE
  - Project Leadership:         1 FTE
 
Total Team Size: ~9 FTE

### 5.4 Phase 4 Dependencies

Critical Path:

- Phases 1-3 all complete and operational

- All project APIs finalized and stable

- Knowledge ingestion pipelines from projects ready

Integration Points:

- NKA ← All projects (ingests operational knowledge)

- All projects ← NKA (use semantic search for decision support)

- Unified portfolio intelligence emerges

### 5.5 Demo Environment Timeline (Phase 4)

Target Go-Live: End of Month 10 (Week 44)

| Week | Component | Status | Audience |
| --- | --- | --- | --- |
| W40 | NKA Knowledge graph | ✓ First 10K entities + relationships | Data team |
| W43 | NKA Semantic search | ✓ Natural language queries working | Engineering team |
| W44 | Public Demo | ✓ Unified intelligence platform | Company all-hands (100+) |
| W48 | Production Launch | ✓ All projects + NKA live | All users |

Demo Script (M10 Public Demo):

- Show unified network intelligence dashboard

- Ask NKA question: "What caused the last 3 incidents involving database latency?"

- Watch semantic search retrieve relevant incidents + RCAs

- Show knowledge graph visualization (relationship between components, incidents, policies)

- Demonstrate incident resolution suggestion (based on similar past incidents)

- Ask "What's the impact of restarting this service?" → BRA + NKA reasoning

- Show knowledge-driven anomaly explanation

- Slack bot integration demo (ask questions from chat)

- Show continuous learning (new incident automatically updates knowledge)

- Q&A

---

## 6. Cross-Cutting Themes

### 6.1 Data Quality & Governance (All Phases)

Initiatives:

- Data validation rules for all pipelines

- Automated data quality scorecards (published weekly)

- Master data management (deduplicate entities across projects)

- Data retention policies (see AMDL document)

Budget: 10% overhead across all phases

Owner: Chief Data Officer / Data Governance office

### 6.2 Security & Compliance (All Phases)

Initiatives:

- Role-based access control (who can execute remediation policies?)

- Audit logging (all AMDL operations recorded)

- Encryption in transit + at rest

- SOC 2 / ISO 27001 readiness

- Incident response integration (when AI detects security incident)

Budget: 8% overhead across all phases

Owner: Chief Security Officer / Security team

### 6.3 Observability & Performance (All Phases)

Initiatives:

- Distributed tracing across project APIs

- Performance SLI/SLO for each project

- Cost tracking (ML inference cost, storage, compute)

- Operational dashboards (team health, pipeline health)

Budget: 7% overhead across all phases

Owner: Platform Engineering / SRE team

### 6.4 User Experience & Adoption (All Phases)

Initiatives:

- Training programs (AI operations concepts, how to use each tool)

- User feedback loops (surveys, interviews, usage analytics)

- Gradual rollout (demo → staging → production)

- Escalation procedures (when to trust AI, when to override)

Budget: 5% overhead across all phases

Owner: Product Management / Operations team

---

## 7. Resource Summary

### 7.1 Overall Staffing Plan

| Role | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Avg |
| --- | --- | --- | --- | --- | --- |
| Data Scientists | 2 | 1.5 | 0 | 0 | 0.9 |
| ML/NLP Engineers | 0.5 | 1.5 | 0 | 1 | 0.75 |
| Backend Engineers | 2 | 4 | 2 | 3 | 2.75 |
| Frontend Engineers | 1 | 0.5 | 0.5 | 1 | 0.75 |
| Data Engineers | 3 | 1.5 | 1.5 | 1 | 1.75 |
| Network Engineers | 0 | 0.5 | 0 | 0 | 0.125 |
| Architects | 1 | 2 | 1 | 1 | 1.25 |
| DevOps/Infra | 1 | 1 | 1.5 | 0.5 | 1 |
| QA/Test | 0.5 | 1.5 | 0 | 0 | 0.5 |
| Product/Leadership | 0.5 | 1 | 0 | 1 | 0.625 |
| TOTAL | 11 | 12 | 6 | 9 | ~9.5 avg |

Total Person-Years: 11 + 12 + 6 + 9 = 38 person-years

### 7.2 Budget Summary

| Phase | Project Costs | Infrastructure | Training | Contingency | **Total** |
| --- | --- | --- | --- | --- | --- |
| Phase 1 | $160K | $40K | $5K | $30K | $235K |
| Phase 2 | $200K | $50K | $10K | $40K | $300K |
| Phase 3 | $200K | $40K | $8K | $35K | $283K |
| Phase 4 | $245K | $45K | $15K | $50K | $355K |
| TOTAL | $805K | $175K | $38K | $155K | $1,173K |

---

## 8. Milestone Timeline & Go/No-Go Gates

### 8.1 Phase 1 Go/No-Go Gate (Month 3, Week 12)

Decision Point: Proceed to Phase 2 (AOA, SHN)?

Success Criteria:

- ✓ PCI forecasts MAPE < 10% for 2+ weeks

- ✓ ICR correlation accuracy validated > 85% on 50+ incidents

- ✓ RCA top-1 accuracy > 50%

- ✓ Demo completed with positive feedback (90%+ executive approval)

- ✓ No critical production incidents caused by new systems

- ✓ Data quality score > 95%

Go Decision: Proceed → Phase 2 Green Light

No-Go Contingency: 2-week remediation cycle, re-evaluate (likely still go, with minor fixes)

Responsibilities: Steering Committee (CTO, VP Ops, VP Engineering)

---

### 8.2 Phase 2 Go/No-Go Gate (Month 6, Week 24)

Decision Point: Proceed to Phase 3 (BRA)?

Success Criteria:

- ✓ AOA policies executing with >75% effectiveness

- ✓ SHN healing success rate > 85%

- ✓ Zero critical incidents caused by autonomous operations

- ✓ Operator approval queue SLA met (>95% within 5 min)

- ✓ Demo completed; stakeholder confidence > 90%

- ✓ Scaling tests validate production readiness

Go Decision: Proceed → Phase 3 Green Light

No-Go Contingency: Enhanced safety controls + 4-week hardening, re-evaluate

Responsibilities: Steering Committee + Ops Leadership

---

### 8.3 Phase 3 Go/No-Go Gate (Month 9, Week 36)

Decision Point: Proceed to Phase 4 (NKA)?

Success Criteria:

- ✓ BRA impact queries respond < 1 sec (p95)

- ✓ Impact accuracy > 80% vs. actual incidents

- ✓ Risk-aware policies reduce mean blast radius by 20%

- ✓ Demo completed; architectural alignment confirmed

- ✓ Governance/lifecycle framework deployed

- ✓ Production readiness audit passed

Go Decision: Proceed → Phase 4 Green Light

No-Go Contingency: Knowledge assistant deployment delayed to Q2 2027

Responsibilities: Steering Committee + Architecture Council

---

### 8.4 Phase 4 Launch Readiness (Month 12, Week 48)

Decision Point: Go-live NKA + integrated portfolio to production?

Success Criteria:

- ✓ NKA semantic search accuracy > 85%

- ✓ Incident resolution suggestion accuracy > 70%

- ✓ Knowledge graph contains > 100K entities

- ✓ All projects APIs stable and integrated

- ✓ Disaster recovery tested

- ✓ User acceptance testing > 90% pass rate

- ✓ Executive sign-off obtained

Go Decision: Production Launch (Week 48)

No-Go Contingency: Extended staging period (4 weeks), slower rollout

Responsibilities: Steering Committee + Program Management Office

---

## 9. Risk Management

### 9.1 Top Risks & Mitigation

| Risk | Severity | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Data quality issues | High | Medium | Early validation, weekly scorecards, automated checks |
| Autonomous operations cause outages | Critical | Low | Human-in-the-loop, blast radius gating, staging testing |
| Scope creep / timeline slippage | High | High | Strict scope control, weekly tracking, phase gates |
| Team attrition | Medium | Medium | Competitive salaries, growth opportunities, mentorship |
| Dependency on external systems | Medium | Medium | SLA agreements, fallback procedures, alternative vendors |
| Security/compliance gaps | High | Low | Early security review, compliance checklist, penetration tests |

### 9.2 Escalation Procedures

Steering Committee escalates to:

- Phase 1 Issues → CTO + VP Ops (weekly sync)

- Phase 2 Issues → CTO + VP Ops + Chief Architect (bi-weekly)

- Phase 3 Issues → CTO + Chief Operating Officer (weekly)

- Phase 4 Issues → CTO + COO + CEO (if go/no-go at risk)

---

## 10. Success Metrics & KPIs

### 10.1 Portfolio-Level KPIs

| KPI | Baseline | Phase 1 Target | Phase 4 Target | Owner |
| --- | --- | --- | --- | --- |
| Mean Time to Resolution (MTTR) | 60 min | 45 min | 15 min | Ops |
| Incident Detection Latency | 10 min | 5 min | 1 min | ICR PM |
| Capacity Planning Accuracy | 70% | 85% | 95% | PCI PM |
| Autonomous Action Success Rate | 0% | 70% | 85%+ | AOA PM |
| Network Self-Healing Rate | 0% | 50% | 80%+ | SHN PM |
| Blast Radius Prediction Accuracy | N/A | N/A | 85% | BRA PM |
| Unplanned Downtime Reduction | Baseline | -30% | -60% | CTO |
| Operator Context-Switching | 15x/day | 10x/day | 3x/day | Ops leadership |
| Team Confidence in AI Systems | 30% | 70% | 90%+ | HR / Culture |

### 10.2 Per-Project KPIs

See individual section deliverables (e.g., 2.2.1 for PCI, 2.2.2 for ICR, etc.)

---

## 11. Communication & Governance

### 11.1 Steering & Oversight

Steering Committee (Monthly)

- CTO, VP Operations, VP Engineering, Chief Product Officer

- Agenda: Phase progress, go/no-go gates, risk review, budget tracking

- Cadence: First Monday of each month

Project Leadership (Weekly)

- Project Managers, Tech Leads, Architects

- Agenda: Detailed status, blockers, cross-project dependencies

- Cadence: Every Monday, 10am

Stakeholder Updates (Bi-weekly)

- Broader operations, engineering, product teams

- Agenda: Demo of progress, user feedback, roadmap updates

- Cadence: Every other Wednesday

### 11.2 Demo Schedule (Public)

- M2 (Week 8): Phase 1 Foundation (ICR + PCI)

- M4 (Week 20): Phase 2 Intelligence (AOA + SHN)

- M7 (Week 32): Phase 3 Capabilities (BRA + Risk)

- M10 (Week 44): Phase 4 Knowledge (NKA + Integration)

- M12 (Week 48): Production Launch Celebration

---

## 12. Appendix: Key Definitions

AMDL: Add/Modify/Delete/Lookup — data lifecycle operations

AOA: Autonomous Operations Agent

BRA: Blast Radius Analysis

ICR: Incident Correlation & Root Cause Analysis

NKA: Network Knowledge Assistant

PCI: Predictive Capacity Intelligence

SHN: Self-Healing Network

MTTR: Mean Time to Resolution

SLA: Service Level Agreement

SLI/SLO: Service Level Indicator / Objective

DSL: Domain-Specific Language

ETL: Extract-Transform-Load

KPI: Key Performance Indicator

RCA: Root Cause Analysis

FTE: Full-Time Equivalent

---

## Document Metadata

- Version: 1.0

- Date: 2026-03-21

- Portfolio: CMI NaaP AI Network Intelligence

- Author: Strategy & Portfolio Management

- Distribution: Steering Committee, Project Leadership, Stakeholders

- Next Review: Post Phase 1 Go/No-Go (Month 3)

- Approval Required: CTO, VP Operations, VP Engineering